MS-Project Exercise:  Personal Portfolio – 10 points

Create a Gantt chart for your Personal Portfolio project.

You will want to think about the “Main Tasks” and subtasks for the creation of your portfolio and then keeping the due date for the project in mind, build out the times and durations of the tasks.  There are task below but they are not all of the tasks necessary, you will have to think about the project and add relevant tasks to the project.

The assignment is worth 10points.

Save the project “without baseline”.

- Start Date:				Today’s Date

- Project Mangement

  - resume

  - business cards

  - domain name registration

- Design

  - wireframes

  - sketches/thumbnails

  - preliminary designs

  - design review

  - mockups

  - finalized designs

- Implementation

  - flash/html template

  - cdrom programming

  - web programming

  - content build out

- Quality Assurance (testing)

- Delivery – Site launch			April 6th, 2006

The following are linked:

- Mockups can not be started until wireframes are completed

- Final Designs can not be started until the mockups are completed

Resources:

Assume you are paying yourself $20 per hour to work on this project.

All allocation is for 100% for each task.

Points Breakdown:

1 – saving without baseline

5 – analysis and implementation of tasks and subtask

3 – workflow

1 – posted MPP file on personal imm portal.

The assignment is due in two weeks on Jan 30th.