Simple Budget Analysis:

Background Information:

Project Budget: $40,000

Schedule: 4 months

20 tasks divided evenly over 4 months

cost per task: $2,000

After one month, you complete an analysis of the project and find the following:

Work Completed After One Month: 3 tasks

Cost breakdown:

- Task 1 - $2000

- Task 2 - $3000

- Task 3 - $3000

Answer the following questions:

- What is the original budget and schedule?

- What is the BCWS?

- What is the ACWP?

- What is the BCWP?

- What is the Cost Variance?

- What is the Cost Performance Index?

- What is the Schedule Variance?

- What is the Schedule Performance Index?

- What is the new estimated cost of the project at completion?

- What is the new estimated completion time?