Microsoft Project Terms & Review Sheet

Project management is the process of planning, organizing, and managing tasks and resources to accomplish a defined objective, usually within constraints on time, resources, or cost.

- A project plan can be simple, for example, a list of tasks and their start and finish dates written on a notepad. Or it can be complex, for example, thousands of tasks and resources and a project budget of millions of dollars.

- Microsoft Project helps you to meet the quality, timeframe, and budget goals by analyzing and summarizing information about the project

Project Terminology

- A task is the specific action that needs to be completed

- Duration is the actual amount of time that passes before the task is done.

- Work is the effort required over a period of time to do the task.

- Resource effort is the amount of effort resources are assigned to the task and their allocation

Baseline cost

- The original project cost as shown in the baseline plan. The baseline cost is a snapshot of the cost at the time when the baseline plan was saved. Tracking and comparing baseline costs against actual costs can help you track cost performance and calculate earned value information.

Gantt chart

- A graphical element on the chart portion of the Gantt Chart view representing the duration of a task, each task duration represented as a horizontal bar

Checking the project start and finish date

- The Start Date is the date the project will start

- Finish Date is the date that MS Project calculates the project will finish.

- You can either develop a project from a “Start Date” and work forward or from a “Finish Date” and work backwards.

- The Finish Date is recalculated based the tasks entered and changes the estimated completion times, lag times and work days.

Changing working days

- A project is scheduled according to the Standard calendar; it specifies working time, the hours and days during which work can occur, and non-working time

- Change the Standard Calendar, click Tools on the menu bar, and then click Change Working Time

- To change working and non-working days, click the date on the calendar and then select the appropriate nonworking or working option

Task information

- Task Information can be broken down into: General, Predecessors, Resources, Advanced, and Notes

- Under Constraint type, you can set each task to either an As Soon As Possible, or As Late As Possible, parameter

# Noncritical task

- A task that has slack time and thus can be completed after its end date by the amount of time equal to its slack without delaying the project end date. Slack is the amount of time a task can slip before it affects another task's dates or the project finish date.

# Critical path

- The series of tasks that must be completed on schedule for a project to finish on schedule. Each task on the critical path is a critical task.

# Critical task

- A task that must be completed on schedule for the project to finish on time. If a critical task is delayed, the project completion date might also be delayed. A series of critical tasks makes up a project's critical path.

### Entering recurring tasks

- Click Insert on the menu bar, and then choose Recurring Task.

- You can modify the recurring task based on frequency and stop date.

Entering milestones

- A milestone is significant point in time during the life of a project.

- Enter a milestone, create a new task, and set the duration to zero and a diamond will appear in the project timeline.

- A reference point marking a major event in a project and used to monitor the project's progress. Any task with zero duration is automatically displayed as a milestone; you can also mark any other task of any duration a milestone.

###### Task dependencies, predecessors

- Task dependencies define the relationships between the tasks in a project

- Finish-to-Start dependency, indicates that the first task must be finished before the second one can start

- Linking the tasks in finish-to-start relationships, you establish the required sequence of tasks

- When no dependencies are defined, all tasks start on the project Start Date in as soon as possible scheduling, or finish on the project Finish Date

- The first task in the dependency is called the predecessor task, and the second task is called the successor task

- A predecessor task that must start or finish before another task can start or finish.

- Creating task dependencies will affect both the Start and Finish dates of the linked tasks

##### Lag and lead times

- A delay between tasks that have a dependency. For example, if you need a two-day delay between the finish of one task and the start of another, you can establish a finish-to-start dependency and specify a two-day lag time. You enter lag time as a positive value.

- An overlap between tasks that have a dependency. For example, if a task can start when its predecessor is half finished, you can specify a finish-to-start dependency with a lead-time of 50 percent for the successor task. You enter lead-time as a negative lag value.

- The number of days entered can be expressed as a positive or negative number

Outlining with summary tasks

- Summary Task is a grouping of tasks that logically belong together

- Indenting tasks creates a subtask relationship with the task above it 
 

Work breakdown structure (WBS)

- A hierarchical structure used to organize tasks for reporting schedules and tracking costs. With Microsoft Project, you can represent the work breakdown structure by using task IDs or by assigning your own WBS code to each task.

- To create your WBS code, click Project on the menu bar, point to WBS, and then click Define Code

# Baseline cost

- The original project cost as shown in the baseline plan. The baseline cost is a snapshot of the cost at the time when the baseline plan was saved. Tracking and comparing baseline costs against actual costs can help you track cost performance and calculate earned value information.

# PERT analysis

- PERT (Program, Evaluation, and Review Technique) analysis is a process by which you evaluate a probable outcome based on three scenarios: a best-case, expected-case, and worst-case scenario. The outcome in question may be the duration of a task, its start date, or its finish date.

#### Changing the project view

- MS Project provides different reports and informational views.

- Selecting a new view from the toolbar, will automatically be reflected in calendar, diagram, or relationship format

Printing a chart view

- The chart views of project’s can span multiple pages. Check work using the “preview page” before printing.

- Print Preview mode allows to you scan multiple pages.

- The Legend at the bottom of each page provides information about the bars.

- Print characteristics, including orientation, margins, legend, header, and footer in the Page Setup dialog box using the Print Preview mode.

Exporting a Graphic of Charts

- Edit > Copy Picture allows you to export a GIF of a section of the project chart to post to a web page.

# Save as Web Page

- You can save a Project as a web page, based on the type of report you wish to generate.